## Sheet1
Risk | Effect | Likelihood | Severity | Overall Risk Level (LxS) | Strategy | Mitigation
No Objective | Lack of an objective can have you wandering with no goal. Can be a project killer | 4 | 2 | 8 | Reduce | Have clear objectives from start of project - i.e. make an MVP then add further
Not identifying Risks | Without understanding any risks or having a plan to counter them, it can have a significant impact on the project. | 4 | 5 | 20 | Reduce | Create a risk management strategy to identify overall risk level & have a plan in place to mitigate said risks.
Lack of Communication | Poor communication with client can create problems surrounding the project. | 5 | 3 | 15 | Accept | Although this is an individual task, communication with the client must be constant and clear. IF something is not understood, make them aware.
Data Loss | Always a possibility and could involve losing a completed deliverable. | 3 | 5 | 15 | Avoid | GitHub will be used for Version Control. It will be linked directly to UiPath for quick and easy backups.
Sensitive Data | GDPR risks and must be takenseriously | 5 | 5 | 25 | Avoid | A fake customer database will used to avoid any misapropriation of data.
Absence/Illness | Project delays and perhaps no deliverable | 2 | 3 | 6 | Reduce | Cannot be easily predicted, if you plan to finish the deliverable ahead of time, you can allow for any minor delays should they be necessary
External Issues | Software/Hardware/Network | 3 | 4 | 12 | Accept | Not easily avoided. Keep communication clear with the client.
Incorrect data appropriated | Scraping incorrect data from emails or other human errors can cause automation failures and mishaps with Company data. | 2 | 4 | 8 | Avoid | Ensure the data is thoroughly checked at regular intervals to make sure the relevant data is being obtained.